## Daily
Return to Office (RTO) Plan
Last updated: | 2020-05-07
Ref | Milestone Description (Level 1) | Accountable Owner | RAG Status | Day | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W
|  |  |  | Week | 1 |  |  |  |  | 2 |  |  |  |  | 3 |  |  |  |  | 4 |  |  |  |  | 5 |  |  |  |  | 6 |  |  |  |  | 7 |  |  |  |  | 8 |  |  |  |  | 9 |  |  |  |  | 10 |  |  |  |  | 11 |  |  |  |  | 12 |  |  |  |  | 13 |  |  |  |  | 14 |  |  |  |  | 15 |  |  |  |  | 16 |  |  |  |  | 17 |  |  |  |  | 18 |  |  |  |  | 19 |  |  |  |  | 20 |  |  |  |  | 21 |  |  |  |  | 22 |  |  |  |  | 23 |  |  |  |  | 24 |  |  |  |  | 25 |  |  |  |  | 26 |  |  |  |  | 27 |  |  |  |  | 28 |  |  |  |  | 29 |  |  |  |  | 30 |  |  |  |  | 31 |  |  |  |  | 32 |  |  |  |  | 33 |  |  |  |  | 34 |  |  |  |  | 35 |  |  |  |  | 36
Due Date | time axis 1900-01-02 to 1900-05-31
1 | Governance
1.01 | Leadership Meeting - (Weekly)
1.02 | Programme Team Call - (Bi-Weekly)
1.03 | Ops Leads Call - (Fortnightly)
1.04 | Government Review Point (1) |  |  | 2020-05-07
1.05 | All Staff Comms
1.06 | Government review Point (2) |  |  | 2020-05-28
1.07 | All Staff Comms
2 | Communications
2.01 | Engage internal stakeholders to prepare brief for internal comms plan on RTO
2.02 | Send out business staffing questionnaire
2.03 | Business Comms Plan Drafted
2.04 | Site Comms Plan Drafted
2.05 | Analyse questionnaire results
2.06 | Review first comms draft
3 | Site Readiness Plan
3.01 | Identify staff required to carry out building / site risk assessment
3.02 | Identify critical staff e.g. fire wardens, first aiders in each agency & building services team
3.03 | Identify and agree which building policies need to be created or updated. Owners asigned
3.04 | Identify and agree which HR policies / FAQ need to be created or updated. Owners asigned
3.05 | Internal Team PPE Update (scheduled intervals)
3.06 | Engage right internal stakedholers on back-to-office online training package brief
3.07 | Building & Personal Insurance broker engaged
3.08 | Process & template created for C-19 site risk assessment
3.09 | Complete building risk assessment including report
3.1 | Provide brief for back-to-office online training package
3.11 | Key furloughed facilities staff communicated a return date
3.12 | Review updated building policies and identify gaps
3.13 | Review updated HR policies & identify gaps
3.14 | Review outcomes of Building Risk Assessment
3.15 | Identify room in reception to take staff who fail temp check
3.16 | Key staff required for risk assessmemt back in offiice
3.17 | Insurance Update
3.18 | Identify mechanism for reporting staff C-19 symptoms, sickness
3.19 | Complete all site risk assessment
3.2 | Create process for staff who fail temperature check on arrival at office
3.21 | Programme team review of site risk assessment findings
3.22 | Set-up online site for all C-19 information e.g. policies, framework etc
3.23 | Test online back-to-office training package
3.24 | Building Services team training package created
3.25 | Complete core building services staff fire warden, first aider training
3.26 | Sign off online back-to-office training package
3.27 | Implement recommendations of risk assessment
3.28 | Review implementation of risk assessment measures at site
3.29 | Sign off building use policies
3.3 | PPE Procured and in place at site - including perspex, temp scanner, masks
3.31 | Building services team training completed
3.32 | Deep clean of site completed
3.33 | All building services staff trained on new building use & services
3.34 | All signage put up in building
4 | Business Readiness Plan
4.01 | Remind staff to complete staffing questionnaire
4.02 | Allocate SRO for business RTO
4.03 | Communicate internally your plan for staff return in Phase 2
4.04 | Ask for volunteers for staff who are willing to RTO if needed
4.05 | Identify which staff are fire warden / first aiders or those that are willing to be trained
4.06 | Identify which staff have a medical or other reason as to why they cannot RTO
4.07 | Identify business critical tasks for Phase 2
4.08 | Understand and implement C-19 sickness tracker
4.09 | Businesses to consider individual employment contracts if staff unwilling or unable to RTO
4.1 | Businesses to submit list of staff returning to office in Phase 2 to Group
4.11 | Assess business staff returning in Phase 2 (fire wardens, footplate, building use)
4.12 | Ensure staff have completed the back to work online training if RTO in Phase 2
4.13 | Sign off business staff return numbers
4.14 | Business risk assessment completed
4.15 | Business risk assessment signed off
4.16 | Complete HR assessments if required for critical staff not able / willing to RTO